## Sheet1
Weeks From the Start of Term 3
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Brainstorm Project Idea and Gain Approval
Literature Review
Research Abstractive Summarisation Literature and List 10 Most Important Papers
Write 2 Positives and 2 Criticisms for Each Paper To Build an Argument
Write Introduction and Literature Review
Write Methodology
Second Draft of Literature Review
Finalise
Results and Analysis
Write Up Initial Analysis from Predictions Results
Write Up Analysis from Extrinsic Surveys
Second Draft of Results and Analysis
Write Conclusion and Further Work
Final Draft and Checks
Code
Collect Data From the Websites Suggested from Literature
Research How Data is Normally Cleaned for Abstractive Summarisation
Clean Data
Exploratory Analysis
Find Notebooks to Follow
Apply the current 4 Top Performing Abstractive Summarisation Models
Finetune the Models
Analysis of Saved Predictions from the Models
Collect Data from Extrinsic Surveys
Analyse data from Extrinsic Surveys
Neaten and Upload to Github
Meet with Sajid |  | Friday | Friday |  | Friday |  | Friday |  | Friday |  | Thursday |  | Friday